## Worksheet
Risk Item | Likelihood | Impact | Priority (High/Medium/Low) | Mitigation Action | Responsible Person | Due Date
Data Breach | Medium | High | High | Implement multi-factor authentication and regular security audits. | IT Manager | 2024-06-30
Hardware Failure | Low | Medium | Medium | Replace outdated hardware and schedule preventive maintenance. | Operations Lead | 2024-07-15
Vendor Non-Compliance | Medium | High | High | Conduct vendor security evaluations and contract compliance reviews. | Compliance Officer | 2024-08-30
Natural Disasters | Low | High | High | Develop disaster recovery plan and conduct drills. | Risk Manager | 2024-09-20
Software Malware | High | Medium | High | Install updated antivirus and run regular system scans. | Security Analyst | 2024-06-15