## Worksheet
Risk Item | Risk Level | Likelihood | Impact | Owner | Action Plan | Due Date
Data Breach | High | Medium | High | IT Security Team | Implement multi-factor authentication and conduct quarterly penetration testing. | 2024-04-15
Supply Chain Disruption | Medium | High | <Medium | Procurement Manager | Diversify suppliers and establish backup sourcing agreements. | 2024-04-20
System Downtime | Medium | High | High | Operations Lead | Upgrade server infrastructure and implement automated failover. | 2024-04-18
Compliance Violation | High | Medium | High | Legal & Compliance Officer | Conduct annual compliance audit and train staff on regulatory requirements. | 2024-04-30