## Worksheet
Risk Identification | Risk Description | Likelihood | Impact th> | Risk Level | Mitigation Strategy | Responsible Party | Review Date
Stock Shortage | Insufficient stock levels leading to delayed orders. | High | High | Critical | Implement daily inventory checks and safety stock levels. | Operations Manager | 2024-04-15
Supplier Delay | Delays in delivery from key suppliers. | Medium | High | <High | Diversify supplier base and maintain buffer stock. | Procurement Officer | 2024-04-16
Obsolescence | Products become outdated or no longer in demand. | Low | High | Medium | Regular product review cycle and early warning system. | Product Manager | 2024-04-17
Data Entry Error | Mistakes in recording stock levels or movements. | Medium | Medium | Medium | Implement automated data capture and dual verification. | IT Support Team | 2024-04-18