## Worksheet
Risk Identification | Risk Description | Likelihood | Impact |  | Risk Rating | Mitigation Strategy | Responsible Party | Timeline
Supply Chain Disruption | Unexpected delays or failures in supplier delivery due to natural disasters or geopolitical issues. | High | Critical | High | Establish dual sourcing; maintain safety stock; monitor supplier performance metrics. | Procurement Manager | Quarterly review
Raw Material Price Fluctuations | Unforeseen increases in cost of key raw materials due to market dynamics. | Medium | High | High | Negotiate long-term contracts; explore alternative materials; implement cost-benefit analysis. | Finance Director | Bi-annual review
Supplier Financial Instability | Suppliers may face bankruptcy or financial difficulties, leading to service interruptions. | Medium | High | High | Conduct supplier financial audits; implement exit plans; diversify supplier base. | Risk Officer | Annual assessment
Logistics Delays | Delays in transportation due to weather, traffic, or port congestion. | Medium | Moderate | Medium | Optimize delivery routes; use real-time tracking; maintain buffer days in planning. | Logistics Coordinator | Ongoing monitoring
Quality Control Failures | Defective products reaching the market due to poor quality control. | Low | Critical | High | Enhance inspection procedures; implement ISO standards; conduct regular audits. | Quality Assurance Lead | Continuous improvement