## Worksheet
Task ID | Task Description | Risk Category | Priority Level | Responsible Party | Due Date | Status | Mitigation Strategy | Risk Score (1-10)
RM-001 | Conduct risk assessment for system outages | Operational Risk | High | Risk Management Team | 2024-03-15 | In Progress | Implement redundant servers and real-time monitoring. | 9
RM-002 | Evaluate third-party vendor cybersecurity practices | <External Risk | Medium | Compliance Officer | 2024-04-10 | Not Started | Require SOC 2 certification and audit reports. | 7
RM-003 | Develop incident response plan for data breaches | Security Risk | Critical | IT Security Lead | 2024-03-30 | Planned | Establish escalation path, communication protocols, and forensics team. | 10
RM-004 | Review disaster recovery procedures annually | Operational Risk | Medium | Operations Manager | 2024-05-01 | On Hold | Update recovery tests based on recent system changes. | 6