## Worksheet
Task ID | Risk Description | Risk Level | Owner | Due Date | Status | Mitigation Plan | Response Strategy | Monitoring Frequency | Last Updated
RM-001 | System outage due to server failure | High | John Doe | 2024-04-15 | In Progress | Backup server activation with failover testing | Automatic failover and manual intervention if needed | Daily | 2024-03-28
RM-002 | Data breach via unsecured API endpoints | Critical | Sarah Lee | 2024-05-10 | Not Started | Implement API encryption and access controls | Immediate patching with audit logs enabled | Weekly | 2024-03-28
RM-003 | Third-party vendor performance failure | Medium | Michael Chen | 2024-06-01 | Planned | Establish SLA with vendor and alternative vendor onboarding | Escalate if performance drops below 95% | Bi-weekly | 2024-03-28
RM-004 | Regulatory non-compliance risk | High | Emily Wang | 2024-07-15 | In Review | Conduct compliance audit and update policies | <Policies to be reviewed quarterly with external auditor | Quarterly | 2024-03-28