## Worksheet
Task ID | Task Description | Risk Category | Responsible Party | Priority Level | Due Date | Status | Risk Score | Mitigation Plan
RM-001 | Conduct initial risk assessment for new project launch. | Operational | Project Manager | High | 2024-03-15 | In Progress | 7.5 | Review stakeholder feedback and implement early warning protocols.
RM-002 | Develop contingency plan for supply chain disruptions. | Supply Chain | Operations Director | Medium | 2024-04-10 | Not Started | 6.2 | Identify alternate suppliers and establish inventory buffer.
RM-003 | Perform security audit on all critical systems. | Security | IT Security Team | High | 2024-03-28 | Completed | 9.1 | All vulnerabilities patched and access logs reviewed.
RM-004 | Train employees on data protection policies. | Compliance | HR Department | Medium | 2024-04-05 | Scheduled | 5.8 | Quarterly training modules delivered via online platform.