## Worksheet
Task ID | Risk Description | Risk Level | Assigned To | Due Date | Status | Priority | Actions Taken
RISK-001 | Failure of critical server during peak hours | High | John Smith | 2023-10-15 | In Progress | High | Backup server testing completed
RISK-002 | Data breach due to outdated software | Critical | Anna Lee | 2023-11-01 | Not Started | Critical | Software audit scheduled for next week
RISK-003 | Vendor non-compliance with security policies | Medium | Robert Chen | 2023-10-30 | On Hold | Medium | Contract review underway
RISK-004 | Insufficient access controls in new application | High | Sarah Kim | 2023-11-10 | Not Started | High | Security review and remediation plan in progress