## Worksheet
Task ID | Risk Description | Risk Level | Owner | Due Date | Status | Mitigation Plan | Review Date
RM-001 | Failure of critical server backup system | High | John Smith | 2024-04-15 | In Progress | Implement redundant backup servers and automated verification checks. | 2024-05-15
RM-002 | Data breach due to outdated software | High | Anna Lee
RM-003 | Network downtime during peak hours | Medium | Mike Chen | 2024-05-10 | Not Started | Deploy load-balancing infrastructure and conduct stress tests. | 2024-06-10
RM-004 | Insufficient employee training on security protocols | Medium | Sarah Wong | 2024-05-01 | Planned | Conduct quarterly security awareness workshops and certification. | 2024-06-01