## Worksheet
Task ID | Risk Description | Risk Level | Owner | Due Date | Status | Mitigation Plan | Monitoring Frequency
RISK-001 | Failure of backup systems during peak load | High | John Smith | 2024-03-15 | In Progress | Implement redundant servers and automated failover protocol. | Weekly
RISK-002 | Data breach due to outdated software | Critical | Anna Lee | <2024-03-10 | Pending Review | Conduct vulnerability scan and upgrade all software to latest patch version. | Bi-weekly
RISK-003 | Supply chain disruption from vendor failure | Medium | Mark Davis | 2024-04-05 | Not Started | Identify alternate suppliers and establish backup agreements. | Monthly
RISK-004 | Compliance failure with GDPR regulations | High | Sarah Chen | 2024-03-25 | On Hold | Conduct compliance audit and update privacy policy documentation. | Quarterly