## Worksheet
Date | Risk Identified | Risk Level | Owner | Mitigation Plan | Status | Next Review Date
Mon, Apr 8, 2024 | Server downtime due to hardware failure | High | IT Department | Deploy redundant servers and scheduled maintenance checks | In Progress | Apr 15, 2024
Tue, Apr 9, 2024 | Data breach due to outdated software | High | Security Team | Update all software and implement multi-factor authentication | Pending Action | Apr 16, 2024
Wed, Apr 10, 2024 | Third-party vendor reliability issues | Medium | Procurement Office | Conduct vendor performance audit and sign SLAs | Not Started | Apr 20, 2024
Thu, Apr 11, 2024 | Employee access to sensitive data | Medium | HR & Compliance | Review role-based access control policies | Planned | Apr 18, 2024
Fri, Apr 12, 2024 | Network latency during peak hours | Low | Network Team | Optimize routing and increase bandwidth allocation | Not Started | Apr 19, 2024