## Worksheet
Date | Activity | Time Spent (hrs) | Risk Identified | Mitigation Plan | Owner | Status
2024-04-01 | Project Risk Assessment Meeting | 3.5 | Third-party vendor delays | Backup supplier agreement signed; buffer time added to timeline. | Alex Johnson | Completed
2024-04-05 | Security Audit Review | 2 | Data breach vulnerability in API | Implement OAuth 2.0 authentication; conduct penetration testing. | Sarah Kim | In Progress
2024-04-10 | Compliance Gap Analysis | 4 | Non-compliance with GDPR Article 30 | Update data processing policy; provide employee training. | Michael Torres | Pending Review
2024-04-15 | Incident Response Drill | 3 | Inadequate incident escalation path | Revise escalation matrix; assign clear roles per tier. | Linda Patel | Completed