## Worksheet
Date | Task Description | Risk Identified | Impact Level | Mitigation Plan | Owner | Status
2024-04-01 | System Upgrade Implementation | Data loss during migration | Medium | Backup before upgrade; rollback protocol in place | Jane Doe | In Progress
2024-04-05 | Third-party Vendor Audit | Vendor non-compliance with security policy | High | Re-evaluate vendor contract; initiate audit follow-up | John Smith | Pending
2024-04-10 | Network Security Patch Deployment | Unpatched vulnerability in firewall | High | Apply patches immediately; monitor logs post-deployment | Alex Johnson | Completed
2024-04-15 | Client Data Access Review | Excessive permissions granted | Medium | Revise access rights using principle of least privilege | Sarah Lee | Planned