## Worksheet
Date | Task | Risk Identified | Impact Level | Likelihood | Mitigation Plan | Owner | Status
2024-04-01 | System Upgrade Deployment | Data loss during rollback | High | Medium | Backup before deployment; test rollback in staging | Alex Morgan | In Progress
2024-04-05 | Third-party Vendor Audit | Vendor data breach vulnerability | Medium | High | Enforce encryption; require SOC 2 certification | Samantha Lee | Pending Review
2024-04-10 | Cloud Infrastructure Scaling | Downtime during peak hours | High | Low | Schedule scaling during off-peak; implement auto-scaling policies | Jordan Patel | Planned
2024-04-15 | Security Patch Rollout | Patch failure in production | Medium | High | Apply patches in stages; monitor post-implementation | Taylor Reed | Completed