## Worksheet
Date | Task Description | Time Spent (hrs) | Risk Identified | Mitigation Strategy | Owner | Status
2024-04-01 | Assessment of third-party vendor compliance | 3.5 | Non-compliance with data protection policies | Implement contractual clauses and quarterly audits | Alex Johnson | Pending Review
2024-04-03 | Security patch deployment in production environment | 2 | Service disruption during deployment | Schedule during off-peak hours with rollback plan | Sarah Chen | Completed
2024-04-05 | Review of access controls for sensitive data | 4 | Excessive privilege assignments | Implement principle of least privilege and role-based access review | Marcus Lee | In Progress
2024-04-08 | Incident response drill for data breach simulation | 3 | Inadequate communication protocol during incident | Establish real-time alerting and escalation matrix | Lena Torres | Completed
2024-04-10 | Documentation of risk exposure for cloud migration | 5 | Data loss due to misconfiguration in S3 buckets | Enable versioning, encryption, and automated monitoring policies | David Kim | Pending Review