## Worksheet
Date | Task Description | Time Spent (hrs) | Risk Identified | Mitigation Plan | Owner | Status
2024-04-01 | Conduct risk assessment for project delivery timeline | 3.5 | Delays due to third-party dependencies | Establish buffer time and alternate suppliers | Alex Johnson | In Progress
2024-04-03 | Review cybersecurity protocols for cloud infrastructure | 2 | Unencrypted data exposure in API calls | Implement TLS 1.3 and mandatory tokenization | Sarah Kim | Completed
2024-04-05 | Assess vendor compliance with GDPR | 4 | Non-compliance in data processing logs | Request audit report and update contracts | Marcus Lee | Pending Review
2024-04-08 | Conduct emergency response drill for data breach | 3 | Inadequate incident response time | Update incident escalation workflow and assign 24/7 on-call team | Emily Zhang | Completed
2024-04-10 | Evaluate risk of project scope creep | 2.5 | Unapproved change requests increasing timeline | Enforce formal change control board approval process | Daniel Reed | In Review