## Worksheet
Date | Activity | Risk Identified | Impact Level | Likelihood | Mitigation Plan | Owner (Manager) | Status
2024-04-01 | Project Launch Meeting | Scope creep due to stakeholder changes | High | Medium | Implement change control board and formal approval workflow | Sarah Johnson | In Progress
2024-04-05 | Vendor Onboarding Review | Vendor delivery delays | Medium | High | Diversify vendor list and set SLAs with penalties for delay | Michael Chen | Pending Action
2024-04-10 | Security Audit Preparation | Data breach vulnerability in legacy system | High | High | Migrate to encrypted platform; conduct penetration testing quarterly | Lisa Rodriguez | Planned
2024-04-15 | Budget Review Session | Unplanned cost escalation in Q3 | Medium | Medium | Establish dynamic budget forecasting model and monthly reallocation reviews | David Kim | Under Review