## Worksheet
Date | Activity | Risk Identified | Impact Level | Likelihood th> | Mitigation Plan | Owner | Status
2023-10-01 | Project Launch Review | Budget overrun risk | High | Medium | Conduct cost-benefit analysis and revise scope. | Sarah Johnson | In Progress
2023-10-05 | Vendor Onboarding | Data breach risk | High | Medium | Implement encryption and multi-factor authentication. | David Chen | Planned
2023-10-10 | Team Training Session | Skill gap risk | Medium | Low | Provide refresher courses and certification access. | Lisa Park | Completed
2023-10-15 | System Upgrade | Downtime risk | High | High | Schedule maintenance during off-peak hours; backup systems ready. | Mike Turner | In Progress
2023-10-20 | Change Request Review | Scope creep risk | Medium | Medium | Implement change control process and approvals. | Emily Reed | Pending