## Worksheet
Date | Time Spent (hours) | Activity Description | Risk Identified | Mitigation Strategy | Owner | Status (Pending/Completed)
2024-04-01 | 3.5 | Conduct risk assessment for project delivery timeline | Potential delay due to third-party vendor failure | Identify backup vendors and include contingency in planning | Jane Smith | Completed
2024-04-05 | 2 | Review security protocols for data handling | Data breach risk due to outdated encryption standards | Implement AES-256 encryption and conduct staff training | John Doe | Pending
2024-04-10 | 4 | Analyze supply chain vulnerabilities | Dependency on single supplier for critical components | Establish dual sourcing strategy and evaluate alternatives | Lisa Chen | Completed
2024-04-15 | 3 | Monitor compliance with regulatory changes (GDPR) | Risk of non-compliance leading to penalties | Conduct quarterly audits and update policies accordingly | Marcus Lee | Pending
Total Time Spent: |  |  | 12.5 hours