## Worksheet
Date | Task Description | Risk Identified | Risk Level (Low/Medium/High/Critical) | Mitigation Strategy | Responsible Person | Estimated Time (hrs) | Status
2023-10-05 | System upgrade planning | Service downtime during deployment | High | Implement rollback protocol and conduct pre-deployment testing | Alex Morgan | 4.5 | In Progress
2023-10-06 | Security audit of access logs | Unauthorized access attempts detected | Critical | Enforce MFA and restrict log-in from non-approved IPs | Sara Patel | 3 | Completed
2023-10-08 | Vendor contract review | Service SLA not meeting expected performance | Medium | Negotiate revised SLA with vendor and implement monitoring alerts | David Kim | 2 | Pending Review
2023-10-10 | Disaster recovery test | Failure to restore data within 30 minutes | High | Optimize backup scripts and schedule failover drills bi-weekly | Julia Reyes | 5 | Planned