## Worksheet
Date | Activity | Duration (hrs) | Risk Identified | Mitigation Strategy | Responsible Person | Status
2024-04-01 | Conduct risk assessment for project launch | 4.5 | Delays in stakeholder feedback | Schedule weekly check-ins with stakeholders | Jane Smith | In Progress
2024-04-05 | Review security vulnerabilities in software | 3 | Data exposure risk | Implement encryption and access controls | Mike Johnson | Completed
2024-04-10 | Analyze supply chain dependencies | 5 | Vendor failure risk | Diversify supplier base and establish backup plans | Sarah Lee | Pending Review
2024-04-15 | Update emergency response plan | 2.5 | Communication breakdown during crisis | Create escalation matrix and test drills quarterly | David Brown | Completed
Risk Management Time Tracker – Report Version