## Worksheet
Date | Time Spent (hrs) | Activity Description | Risk Identified | Mitigation Plan | Responsible Person
2024-04-01 | 2.5 | Review of project timeline for delays | Uncertain delivery dates affecting stakeholder trust | Update schedule with buffer time and weekly reviews | John Smith
2024-04-03 | 1.5 | Assessment of vendor reliability | Vendor may fail to deliver critical components on time | Identify backup suppliers and negotiate SLAs | Sarah Lee
2024-04-05 | 3 | Security audit of system access logs | Unauthorized access detected in test environment | Implement role-based access control and monitor logs hourly | Mike Chen
2024-04-08 | 2 | Team risk workshop on project scope creep | Uncontrolled changes leading to increased costs | Create formal change request process and approval chain | Lisa Wong