## Worksheet
Date | Task | Time Spent (hrs) | Risk Identified | Mitigation Plan | Owner | Status
2024-04-01 | Onboarding new team member | 3.5 | Data access permissions misaligned | Implement role-based access control (RBAC) | Ana Rodriguez | In Progress
2024-04-03 | Code review for v2.1 release | 5 | Potential security vulnerability in API endpoint | Patch endpoint and perform penetration test | Jake Chen | Completed
2024-04-05 | Stakeholder meeting – budget review | 2 | Scope creep risk in project timeline | Define change control process and freeze scope post-review | Sophia Lee | Planned
2024-04-07 | System outage response (3-hour downtime) | 3.5 | Backup systems not activated on time | Update failover procedures and conduct monthly drills | David Kim | Post-Mortem Completed