## Worksheet
Date | Activity | Time Spent (hrs) | Risk Identified | Mitigation Action | Responsible Person | Status
2024-04-01 | System security audit | 3.5 | Unauthorized access risk | Implement multi-factor authentication (MFA) | Alex Turner | In Progress
2024-04-05 | Vendor risk assessment | 2 | Data breach vulnerability | Review contract clauses and require SOC 2 compliance | Samantha Lee | Pending Approval
2024-04-10 | Backup integrity check | 1.5 | Incomplete backup restoration risk | Schedule automated daily backups with verification logs | Jordan Park | Completed
2024-04-15 | Emergency response plan review | 4 | Lack of clear incident escalation path | Update escalation matrix and conduct tabletop exercise | Taylor Reed | Planned