## Worksheet
Risk Item | Risk Level | Owner | Due Date | Status | Action Required
System Downtime During Peak Hours | High | IT Operations Team | 2024-04-15 | Pending Review | Conduct load testing and implement auto-scaling.
Data Breach Due to Legacy System | High | Security Compliance Officer | 2024-05-01 | In Progress | Initiate migration plan and phase out legacy access.
Vendor Non-Compliance with SLAs | Moderate | Procurement Manager | 2024-04-30 | To Do | Review vendor contracts and renegotiate SLAs.
End-User Training Gaps | Low | Training Coordinator | 2024-06-10 | Pending Approval | Schedule and approve training modules for Q2.
Third-Party API Integration Failure | High | Development Lead | 2024-05-15 | Blocked | Wait for API provider to resolve authentication issues.