## Worksheet
Risk Identification | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Mitigation Strategy | Responsible Party | Due Date | Status
Inventory Theft | Unauthorized removal of goods from warehouse premises. | 4 | 5 | 20 | Install surveillance cameras and access controls. | Security Manager | 2024-06-30 | Active
Equipment Failure | Failure of critical warehouse equipment (e.g., forklifts, lifts). | 3 | 4 | <12 | Regular maintenance schedule and backup equipment. | Operations Supervisor | 2024-07-15 | Planned
Supply Chain Disruption | Delays or interruptions in inbound shipments. | 5 | 4 | 20 | Develop alternative suppliers and buffer stock strategy. | Procurement Lead | 2024-08-10 | Active
Fire Hazard | Flammable materials stored improperly leading to fire risk. | 4 | 5 | 20 | Conduct fire safety audits and reorganize storage zones. | Safety Officer | 2024-09-01 | Pending Review
Data Breach | Unauthorized access to warehouse inventory records. | 3 | 5 | 15 | Implement role-based access control and encryption. | IT Administrator | 2024-07-25 | Active