## Worksheet
Risk Identification | Risk Category | Likelihood | Impact th> | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Review Date
Supply Chain Disruption | Operational Risk | High | High | 9 | Diversify suppliers; maintain safety stock | Procurement Manager | 2024-06-30
Inventory Theft | Security Risk | Medium | High | 6 | Install surveillance; conduct regular audits | Warehouse Supervisor | 2024-07-15
Equipment Failure | Technical Risk | High | Medium | 6 | Schedule preventive maintenance; backup systems | Maintenance Team Lead | 2024-08-01
Weather-Related Delays | Environmental Risk | Medium | Medium | 3 | Monitor weather forecasts; adjust delivery schedules | Logistics Coordinator | 2024-09-10
Data Breach in Inventory System | Information Risk | Low | High | 3 | Implement encryption; access controls and training | IT Security Officer | 2024-10-05