## Worksheet
Risk Identification | Risk Description | Risk Category | Likelihood (1-5) | Impact (1-5) | Current Controls | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Due Date
Stock Loss Due to Theft | Unauthorized removal of inventory from warehouse premises. | Security | 4 | 5 | Night patrols, CCTV monitoring. | 20 | Install additional surveillance and improve access control. | Security Manager | 2024-06-30
Equipment Failure | Malfunction of inventory handling machinery. | Operations | 3 | 4 | Scheduled maintenance, vendor support. | 12 | Implement predictive maintenance schedule. | Operations Lead | 2024-07-15
Poor Inventory Accuracy | Discrepancies between physical stock and system records. | Process Control | 2 | 3 | Regular audits, reconciliation procedures. | 6 | Enhance cycle counts and digitize inventory logs. | Inventory Controller | 2024-08-10
Weather-Related Damage | Damage to stored goods due to extreme weather. | Environmental | 3 | 4 | Warehouse coverings, climate control. | 12 | Improve warehouse sheltering and monitoring systems. | Facilities Manager | 2024-09-05
Supplier Delivery Delays | Unplanned delays in incoming goods affecting stock levels. | Supply Chain | 4 | 3 | Backup suppliers, delivery tracking. | 12 | Diversify supplier base and establish buffer stock. | Procurement Officer | 2024-10-15