## Worksheet
Date | Risk Item | Likelihood (1-5) | Impact (1-5) | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Person | Due Date | Status
2023-10-03 | System Downtime | 4 | 5 | 20 | Implement redundant servers and automated failover | IT Manager | 2023-10-10 | In Progress
2023-10-03 | Data Breach | 3 | 4 | 12 | Enhance encryption and access controls | Security Officer | 2023-10-15 | Planned
2023-10-03 | Vendor Failure | <2 | 3 | 6 | Identify backup vendors and SLA review | Operations Lead | 2023-10-08 | Completed
2023-10-03 | Regulatory Non-Compliance | 5 | 5 | 25 | Conduct quarterly audits and staff training | Compliance Officer | 2023-10-25 | Not Started