## Worksheet
Week | Risk Identification | Risk Assessment (Likelihood & Impact) | Mitigation Strategy | Responsible Party | Timeline | Status
Week 1 | System downtime due to hardware failure | Likely (Medium), Impact: High | Implement redundant servers and regular monitoring | IT Department | April 1 - April 7 | Pending Action
Week 2 | Data breach due to weak authentication | Likely (Medium), Impact: Critical | Enforce multi-factor authentication and audit logs | Security Team | April 8 - April 14 | In Progress
Week 3 | Third-party vendor delay | Unlikely (Low), Impact: Medium | Establish backup vendors and SLA monitoring | Procurement Office | April 15 - April 21 | Planned
Week 4 | Regulatory non-compliance due to policy gap | Likely (High), Impact: High | Conduct compliance review and update policies | Legal & Compliance Team | April 22 - April 28 | Urgent Action Required
Week 5 | Staff turnover leading to knowledge loss | Unlikely (Low), Impact: Medium | Implement knowledge transfer documentation | HR & Training Department | April 29 - May 5 | To Be Determined