## Worksheet
Date | Risk Identifier | Risk Description | Likelihood | Impact | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Action Deadline | Status
Monday, April 8, 2024 | R-001 | System downtime due to unpatched vulnerabilities | High | High | 9 | Implement automated patch management and scheduled vulnerability scans. | IT Security Team | April 25, 2024 | In Progress
Tuesday, April 9, 2024 | R-002 | Data breach due to employee error | Medium | High | 6 | Conduct mandatory data handling training and introduce two-factor authentication. | HR & Compliance Office | April 30, 2024 | Planned
Wednesday, April 10, 2024 | R-003 | Third-party supplier failure | High | Medium | 6 | Establish backup suppliers and conduct quarterly vendor risk assessments. | Procurement Team | May 10, 2024 | Pending Review
Thursday, April 11, 2024 | R-004 | Regulatory change affecting compliance | Medium | Medium | 3 | Monitor regulatory updates and schedule internal audit alignment. | Legal & Compliance Team | April 20, 2024 | Completed
Friday, April 12, 2024 | R-005 | Cyberattack via phishing campaign | High | Very High | 12 | Deploy advanced email filtering and employee awareness programs. | CISO & Training Department | May 5, 2024 | Under Review