## Worksheet
Week | Risk Identifier | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Mitigation Strategy | Responsible Party | Review Date
Week 1 | RI-001 | Failure of critical server infrastructure | 4 | 5 | 20 | Implement redundant servers and auto-recovery protocols | IT Operations Team | 2024-04-01
Week 2 | RI-002 | Supply chain disruption due to geopolitical events | 3 | 4 | 12 | Establish dual suppliers and contingency plans | Procurement & Logistics Team | 2024-04-08
Week 3 | RI-003 | Data breach due to phishing attack | 5 | 5 | 25 | Enhance employee training and deploy advanced email filtering | Security & Compliance Team | 2024-04-15
Week 4 | RI-004 | Regulatory compliance violation | 2 | 5 | 10 | Conduct quarterly compliance audits and update documentation | Legal & Compliance Team | 2024-04-22