## Worksheet
Week | Risk Identification | Risk Assessment (Likelihood & Impact) | Mitigation Strategy | Responsible Party | Timeline | Budget Allocation ($)
Week 1 | Project timeline delays due to external vendor issues | High likelihood, Medium impact | Establish backup vendor agreements and buffer time in planning | Peter Johnson (Project Manager) | January 3–10, 2024 | $5,000
Week 2 | Security breach from outdated software | Medium likelihood, High impact | Immediate software patching and conduct security audit | Sarah Lee (IT Security Lead) | January 10–17, 2024 | $3,500
Week 3 | Resource over-allocation during critical phase | High likelihood, High impact | Implement resource leveling and daily workload tracking | Michael Chen (Operations Lead) | January 17–24, 2024 | $6,000
Week 4 | Compliance audit failure due to documentation gaps | Medium likelihood, High impact | Complete compliance documentation review and update process | Lisa Wong (Compliance Officer) | January 24–31, 2024 | $4,000