## Worksheet
Week | Risk Identified | Risk Level | Potential Impact | Mitigation Strategy | Responsible Party | Due Date | Status
Week 1 | Server downtime during peak hours | High | Loss of revenue, customer dissatisfaction | Deploy redundant servers and auto-scaling | IT Operations Team | 2023-10-15 | In Progress
Week 2 | Data breach due to outdated software | High | Legal penalties, reputational damage | Patch all systems and implement encryption | Security & Compliance Team | <2023-10-22 | Planned
Week 3 | Supply chain delay for key components | Moderate | Project timeline extension | Identify backup suppliers and diversify sourcing | Purchasing Team | 2023-10-29 | Pending Review
Week 4 | Team turnover in product development | Medium | Delays in feature delivery | Offer retention bonuses and mentorship programs | HR & Leadership Team | <2023-11-05 | Not Started