## Worksheet
Week | Team Member | Risk Identified | Impact Level | Likelihood | Risk Score (Impact × Likelihood) | Mitigation Strategy | Responsible Party | Due Date | Status
Week 1 | Alex Johnson | Dependency on external vendor delays | High | Medium | 6 | Develop backup vendor list and SLA monitoring process | Alex Johnson | 2023-10-15 | In Progress
Week 2 | Samantha Lee | Data breach due to outdated software | Critical | High | 12 | Conduct full system audit, apply patch updates, and implement firewall upgrades | Samantha Lee & IT Team | 2023-10-22 | Planned
Week 3 | Jordan Taylor | Resource shortage during peak periods | Medium | High | 6 | Create resource allocation plan and cross-train team members | Jordan Taylor | 2023-10-29 | Pending Approval
Week 4 | Mia Chen | Poor communication between departments | Low | Medium | 3 | Implement weekly sync meetings and shared dashboards | Mia Chen & Operations Team | 2023-11-05 | Not Started