## Worksheet
Date | Risk Identified | Risk Level | Potential Impact | Mitigation Plan | Owner | Status
Monday, Apr 8, 2024 | Server downtime due to outdated software | High | Business disruption and data loss | Update software within next 7 days; schedule patching during off-peak hours | J. Smith | Active
Tuesday, Apr 9, 2024 | Data breach risk from unsecured endpoints | Medium | Loss of sensitive customer information | Implement endpoint encryption and enforce device compliance policy | A. Johnson | Pending Review
Wednesday, Apr 10, 2024 | Third-party vendor security lapse | High | Exposure of internal systems to external threats | Conduct a security audit of vendor; require SOC 2 certification for all critical vendors | M. Lee | Planned
Thursday, Apr 11, 2024 | Insufficient backup procedures | Medium | Extended recovery time after failure | Establish automated daily backups with offsite storage and test recovery monthly | S. Taylor | In Progress
Friday, Apr 12, 2024 | Insider threat from employee access misuse | High | Unauthorized data access or leak | Implement role-based access control and conduct quarterly security awareness training | R. Patel | New Risk Detected