## Worksheet
Week of | Risk Identification | Risk Assessment (Likelihood & Impact) | Risk Owner | Mitigation Strategy | Monitoring & Review Frequency | Action Status
April 7 - April 13, 2024 | System outage due to server overload | Likelihood: Medium ¦ Impact: High | Jane Smith | Implement load balancing and auto-scaling; conduct stress tests weekly. | Bi-weekly | Completed
April 14 - April 20, 2024 | Data breach from unpatched firewall | Likelihood: High ¦ Impact: Critical | Mike Johnson | Apply patches within 72 hours; enable intrusion detection system. | Daily (after incidents) | In Progress
April 21 - April 27, 2024 | Employee data misuse due to poor access control | Likelihood: Medium ¦ Impact: High | Sarah Lee | Enforce role-based access control (RBAC) and conduct quarterly audits. | Quarterly | Planned
April 28 - May 4, 2024 | Third-party vendor failure | <Likelihood: Low ¦ Impact: High | David Chen | Establish SLAs and alternate vendor agreements. | Monthly | Pending Review
May 5 - May 11, 2024 | Compliance gap in data retention policies | Likelihood: Medium ¦ Impact: High | Emma Rodriguez | Update policy documentation and train staff on compliance. | Bi-monthly | Not Started