## Worksheet
Date | Risk Identified | Risk Level | Potential Impact | Mitigation Strategy | Responsible Party | Status (Open/Resolved) | Next Review Date
Monday, May 13, 2024 | Network downtime due to outdated firewall | High | Loss of business operations and customer access | Update firewall configuration; schedule patch cycle | IT Security Team | Open | May 20, 2024
Tuesday, May 14, 2024 | Supply chain delay from third-party vendor | Medium | Delays in product delivery and customer satisfaction drop | Identify backup vendors; create contingency plan | Procurement Manager | Open | May 21, 2024
Wednesday, May 15, 2024 | Data breach due to weak password policy | High | Violation of compliance; reputational damage | Enforce multi-factor authentication and audit logs | Chief Information Officer | Open | May 18, 2024
Thursday, May 16, 2024 | Employee onboarding process inefficiency | Low | Increased training time and onboarding errors | Automate onboarding workflow with digital checklist | HR Department | Open | May 23, 2024
Friday, May 17, 2024 | Server overload during peak hours | Medium | Service slowdowns and poor user experience | Implement load balancing and auto-scaling policies | Systems Engineer Team | Open | May 24, 2024