## Worksheet
Date | Risk Identified | Risk Level | Likelihood | Impact(th) | Potential Cause | Mitigation Strategy | Responsible Person | Monitoring Frequency | Status
Monday, April 1, 2024 | Server downtime during peak hours | High | Medium | High | Inadequate load balancing configuration | Implement auto-scaling and perform load testing weekly | Jane Smith | Weekly review | Ongoing
Tuesday, April 2, 2024 | Data breach due to outdated software | High | High | Very High | Unpatched third-party applications | Enforce patch management policy and quarterly audits | Mike Johnson | Bi-weekly audit | Pending action
Wednesday, April 3, 2024 | Employee phishing susceptibility | Moderate | High | Moderate | Lack of security awareness training | Conduct bi-monthly phishing simulations and training sessions | Sarah Lee | Monthly review | In Progress
Thursday, April 4, 2024 | Outage due to power failure | Medium | Medium | Moderate | No backup generator in place at remote site | Install emergency backup power system by end of quarter | David Kim | Quarterly check | Pending action
Friday, April 5, 2024 | Third-party vendor failure | High | Medium | High | Lack of contract SLAs and redundancy clauses | Negotiate SLAs and establish failover agreements with vendors | Linda Wong | Bi-monthly review | Planned action