## Worksheet
Week of | Risk Identification | Risk Assessment (Likelihood & Impact) | Mitigation Strategy | Responsible Party | Due Date | Status
March 3 - March 7, 2024 | Market volatility affecting portfolio valuations | Likelihood: High ¦ Impact: High | Implement hedging strategies and diversify asset allocation | Financial Analyst Team | March 5, 2024 | Pending Review
March 10 - March 14, 2024 | Regulatory change in compliance reporting | Likelihood: Medium ¦ Impact: High | Update internal compliance protocols and conduct staff training | Compliance Officer | March 12, 2024 | On Track
March 17 - March 21, 2024 | Technology downtime affecting trading systems | Likelihood: Medium ¦ Impact: High | Redundant system deployment and scheduled maintenance plan | IT Operations Lead | March 19, 2024 | In Progress
March 24 - March 28, 2024 | Third-party vendor performance risk | Likelihood: Low ¦ Impact: Medium | Establish SLA monitoring and backup vendor agreements | Vendor Management Team | March 26, 2024 | Not Started
March 31 - April 4, 2024 | Currency exchange rate fluctuations | Likelihood: High ¦ Impact: Medium | Adjust forward contracts and monitor exchange benchmarks daily | Foreign Exchange Manager | April 1, 2024 | Pending Review