## Worksheet
Week | Date Range | Risk Identification | Risk Assessment (Likelihood & Impact) | Mitigation Strategy | Owner | Monitoring & Review
Week 1 | 04/01 – 04/07 | Cybersecurity breach due to outdated software | Likelihood: High ¦ Impact: Critical | Update all systems quarterly; implement endpoint detection | IT Security Lead | Weekly audit logs, bi-weekly vulnerability scans
Week 2 | 04/08 – 04/14 | Supply chain disruption from single vendor dependency | Likelihood: Medium ¦ Impact: High | Identify at least two backup suppliers | Procurement Manager | Monthly supplier performance review
Week 3 | 04/15 – 04/21 | Data privacy violation during employee onboarding | Likelihood: Low ¦ Impact: High | Enforce mandatory training and secure onboarding workflows | HR Director | Quarterly compliance audit with legal team
Week 4 | 04/22 – 04/28 | Operational downtime due to system failure | Likelihood: High ¦ Impact: Medium | Deploy redundant servers and failover protocols | System Architect | Daily system health checks, monthly DR test
Week 5 | 04/29 – 05/05 | Regulatory compliance lag in reporting deadlines | Likelihood: Medium ¦ Impact: Critical | Automate reporting with compliance dashboard | Compliance Officer | Bi-weekly validation against regulatory updates