## Worksheet
Week | Date Range | Risk Identification |  |  | Risk Assessment |  |  | Mitigation Plan |  |  | Owner | Status
|  | New | Existing | Total | Likelihood | Impact | Severity (L×I) | Action Steps | Responsible | Timeline
Week 1 | 01/04/2024 – 07/04/2024 | ✓ | ✗ | 1 | Medium | High | 7 | Conduct stakeholder interviews | Risk Manager A | 2 weeks | Active
Week 2 | 08/04/2024 – 14/04/2024 | ✗ | ✓ | 2 | Low | Medium | 4 | Update security policies | IT Security Lead | 1 week | On Track
Week 3 | 15/04/2024 – 21/04/2024 | ✓ | ✓ | 3 | High | High | 9 | Implement backup protocol | Operations Manager | Immediate | At Risk
Next Week (Week 4)
Week 4 | 22/04/2024 – 28/04/2024 | ✗ | ✗ | 0 | N/A | N/A | 0 | Review mitigation effectiveness | Risk Manager B | Ongoing | Pending Review