## Worksheet
Week of | Risk Identification | Risk Assessment (Likelihood & Impact) | Mitigation Strategy | Responsible Party | Due Date | Status
May 1 - May 7, 2024 | System outage due to server failure | Likelihood: High ¦ Impact: High | Implement redundant servers and automated failover | IT Operations Team | May 3, 2024 | In Progress
May 8 - May 14, 2024 | Third-party vendor data breach risk | Likelihood: Medium ¦ Impact: High | Conduct vendor security audits and sign SLAs with compliance clauses | Risk & Compliance Officer | May 10, 2024 | Planned
May 15 - May 21, 2024 | Insufficient employee training on security protocols | Likelihood: Medium ¦ Impact: Medium | Develop and deploy mandatory security training modules | HR & Security Manager | May 18, 2024 | Scheduled
May 22 - May 28, 2024 | Unauthorized access to sensitive systems | Likelihood: High ¦ Impact: Critical | Enforce multi-factor authentication and role-based access control | Security Team Lead | May 25, 2024 | Pending Approval
May 29 - June 4, 2024 | Regulatory non-compliance due to delayed reporting | Likelihood: Low ¦ Impact: High | Automate compliance reporting with real-time dashboards | Compliance Officer | June 1, 2024 | Not Started