## Worksheet
Week | Risk Identified | Risk Assessment |  |  | Mitigation Plan |  |  | Owner | Status
|  | Likelihood | Impact | Rating | Action Step | Timeline | Responsible Party
Week 1 | System outage due to hardware failure | Medium | High | High (7/10) | Backup servers operational | Implement redundancy by end of month | IT Operations Team | Active
Week 2 | Third-party data breach vulnerability | Low | High | High (8/10) | Update access controls and audit logs | Complete penetration test by Week 4 | Security Team | Planned
Week 3 | Employee phishing attack exposure | Medium | Medium | Moderate (5/10) | Conduct security awareness training | Run campaign in Week 3 and 4 | HR & Security | Active
Week 4 | Regulatory compliance gap in reporting | Low | High | High (6/10) | Review and update reporting process | Finalize by end of quarter | Legal & Compliance | Pending
Week 5 | Supply chain dependency risk | High | Medium | High (9/10) | Diversify key vendor base | Q3 implementation plan | Procurement Team | Planned
Week 6 | Cloud migration service disruption | Medium | High | High (7/10) | Establish failover protocol | Test in Week 5, deploy Week 7 | IT Infrastructure Team | Active
Week 7 | Staff turnover leading to knowledge loss | Low | High | High (8/10) | Implement documentation and onboarding process | Complete by end of quarter | HR & Operations | Pending
Week 8 | Network bandwidth congestion during peak hours | Medium | Medium | Moderate (4/10) | Upgrade network infrastructure | Scheduled for Q3 upgrade cycle | Network Team | Planned
Quarterly Risk Management Weekly Planner – Q1 2024