## Worksheet
Date | Risk Identified | Likelihood | Impact> | Risk Score (L × I) | Mitigation Strategy | Owner | Status
Mon, Apr 15 | Server downtime due to hardware failure | High | Critical | 8 | Implement redundant servers and regular maintenance checks | DevOps Team | Active
Tue, Apr 16 | Data breach from unsecured API endpoint | Medium | High | <6 | Apply authentication tokens and audit access logs | Security Team | In Review
Wed, Apr 17 | Third-party vendor delay in delivery | Low | Medium | 3 | Establish backup suppliers and buffer timelines | Procurement Team | Planned
Thu, Apr 18 | Team burnout due to tight deadlines | Medium | Medium | 4 | Introduce flexible work hours and mental health days | HR Department | Pending Approval