## Worksheet
Week | Team Member | Risk Identified | Impact Level | Likelihood | Mitigation Plan | Owner | Due Date | Status
Week 1 | Alex Johnson | Third-party vendor delay | High | Medium | Engage backup vendor; update SLAs | Sarah Kim | 2023-10-15 | In Progress
Week 2 | Morgan Lee | Data access policy violation | Medium | High | <Conduct staff training; audit permissions | David Wu | 2023-10-22 | Pending Review
Week 3 | Taylor Reed | System downtime during peak hours | High | High | Schedule maintenance off-peak; add auto-recovery | Linda Patel | 2023-10-29 | Planned
Week 4 | Jordan Smith | External cyber threat monitoring gap | High | Medium | Implement SIEM integration; weekly threat reviews | Carlos Mendez | 2023-11-05 | Not Started