## Worksheet
Date | Risk Identified | Risk Level | Impact | Likelihood | Owner | Mitigation Plan | Status | Next Review Date
Mon, Apr 8, 2024 | Data Breach Due to Unpatched Server | High | Critical | Medium | IT Security Team | Implement automatic patching and conduct vulnerability scan weekly. | Active | Apr 15, 2024
Tue, Apr 9, 2024 | Third-Party Vendor Delay in Delivery | Medium | High | Low | Procurement Manager | Identify alternative suppliers and establish backup delivery timeline. | Pending | Apr 16, 2024
Wed, Apr 10, 2024 | System Downtime During Peak Hours | High | Medium | High | Operations Lead | Deploy load balancing and schedule maintenance during off-peak hours. | Planned | Apr 23, 2024
Thu, Apr 11, 2024 | Employee Access to Sensitive Data | Medium | Medium | High | HR & Compliance Officer | Revisit access controls and implement role-based permissions review. | Reviewing | Apr 18, 2024
Fri, Apr 12, 2024 | Compliance Change in New Regulation | High | Critical | Medium | Legal & Compliance Team | Update policies and conduct employee training by next week. | In Progress | Apr 19, 2024