## Sales Forecasting Gantt Chart
Sales Forecasting Gantt Chart (Detailed)
Task ID | Activity/Project | Start Date | End Date | Duration (Days) | Status | Progress (%)
001 | Q4 Product Launch Planning | 2023-10-01 | 2023-11-30 | 60 | Ongoing
002 | Market Research & Competitor Analysis | 2023-10-15 | 2023-11-15 | 31 | Completed
003 | Forecast Modeling & Revenue Projections | 2023-11-01 | 2023-12-15 | 45 | Ongoing
004 | Channel Partner Onboarding | 2023-11-15 | 2023-12-31 | 46 | Delayed
005 | Marketing Campaign Design (Q4) | 2023-11-20 | 2023-12-31 | 41 | Completed
006 | Sales Team Training & Rollout | 2023-12-01 | 2024-01-15 | 45 | Ongoing
007 | Launch Event & PR Campaign | 2024-01-16 | 2024-01-31 | 16 | Delayed
008 | Post-Launch Performance Review | 2024-02-01 | 2024-03-31 | 60 | Ongoing
Total Duration: |  |  |  | 305 | Overall Progress: 68%
Legend:
Ongoing– Task is in progress but not complete.
Completed– Task has been finished successfully.
Delayed– Task is behind schedule.