## Worksheet
Sales Forecasting - Extended Gantt Chart
Task ID | Project Name | Phase / Milestone | Start Date | End Date | Duration (Days) | Status | Progress (%)
Sales Forecasting Q3 2024 - Total Duration: 90 Days ¦ Target Revenue: $1.8M
SR-01 | Sales Forecasting Project | Market Research & Analysis | 2024-07-01 | 2024-07-15 | 15 | Pending / In Progress | 60%
SR-02 | Sales Forecasting Project | Data Collection & Integration | 2024-07-16 | 2024-08-15 | 31 | In Progress | 75%
SR-03 | Sales Forecasting Project | Forecast Model Development | 2024-08-16 | 2024-09-15 | 31 | Pending (Starts 8/16) | 0%
SR-04 | Sales Forecasting Project | Model Validation & Stakeholder Review | 2024-09-16 | 2024-10-31 | 46 | Pending (Starts 9/16) | 0%
SR-05 | Sales Forecasting Project | Final Report & Presentation | 2024-11-01 | 2024-11-30 | 30 | Pending (Starts 11/01) | 0%
M-01 | Sales Forecasting Project | Model Final Approval (Milestone) | 2024-10-31 | 2024-10-31 | - | Milestone Achieved? | ✔️
M-02 | Sales Forecasting Project | Project Final Delivery (Milestone) | 2024-11-30 | 2024-11-30 | - | Milestone Pending? | ⏳
Total Project Duration: |  |  |  |  | 123 Days | Final Forecast Target: $1,800,000 ¦ Actual Forecast Accuracy (Est.): 92%