## Sales Forecasting - Gantt Chart
Sales Forecasting - Gantt Chart (One Page)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status
T001 | Market Research & Analysis | 2024-04-01 | 2024-04-15 | 15 | 85% Complete
T002 | Customer Segmentation | 2024-04-16 | 2024-04-30 | 15 | 75% Complete
T003 | Product Pricing Strategy | 2024-05-01 | 2024-05-10 | 10 | 65% Complete
T004 | Sales Channel Planning | 2024-05-11 | 2024-05-25 | 15 | 90% Complete
T005 | Marketing Campaign Launch | 2024-05-26 | 2024-06-15 | 21 | 50% Complete
T006 | Forecast Validation & Adjustment | 2024-06-16 | 2024-07-31 | 46 | 35% Complete
M001 | Sales Forecast Finalized | 2024-07-31 | 2024-07-31 | - | On Track (Projected)
Total Duration: |  |  |  | 132
Generated on: